## Wieghted Tasks Management
SPRINT 2 REFLECTION
Feature | Tasks | Actual Weightage | Status
Account Management | Frontend: Sign up page UI | 2 | Completed |  | 1 | less than 1hr
| Backend: Implement Signup API (POST /auth/signup) with validation | 2 | Completed |  | 2 | 2-3 hrs
| Backend: Create a user with specific fields and save in DB | 1 | Completed |  | 3 | 4-6 hrs
| Backend: create verify email verification code and send email to use | 1 | Completed |  | 5 | 8-12 hrs
| Frontend: show UI page when user clicks on that link for success message | 1 | Completed |  | 8 | 1 day
| Frontend: Create Login Page UI with email and password fields fields | 2 | Completed |  | 13 | 2+ days
| Backend: Implement Login API (POST /api/auth/login) | 2 | Completed
| Frontend: Create Password Reset Page with email input | 1 | Completed
| Backend: Implement Reset Password API (POST /api/auth/reset-password) | 1 | Completed
| Frontend: Create New Password Page for updating the password | 1 | Completed
| Backend: Update user's password in DB | 1 | Completed
| Frontend: Logout Button | 1 | Completed
| Backend: Clear cookies on logout | 2 | Completed
| Backend: Implement Logout API (POST /api/auth/logout) | 2 | Completed
| Frontend: Redirect users to the login page after logout | 1 | Completed
| Frontend: Fetch user role from backend after login | 1 | Completed
| Frontend: Implement role-based navigation (Employer vs. Candidate) | 2 | Completed
| Frontend: Hide unauthorized features | 1 | Completed
| Backend: Store user roles in MongoDB | 1 | Completed
| Backend: Implement middleware to enforce role-based access control | 3 | Completed
| Frontend: Create Profile Page | 3 | Completed
| Backend: Implement User Profile API | 3 | Completed
| Backend: Store user details | 2 | Completed
Employer Portal | Frontend: UI for Job Posting Creation | 1 | Completed
| Backend: API for Job Posting | 2 | Completed
| Frontend: UI for Applicant Tracking | 2 | Completed
| API for Viewing Applicants | 2 | Completed
| Frontend: Enable employers to update company details | 2 | Completed
Candidate Portal | Frontend: Create UI for a page showing all available job postings | 1 | Completed
| Backend: Implement GET /api/jobs to fetch job postings | 2 | Completed
| Frontend: Add an "Apply" button on job postings | 1 | Completed
| Frontend: Clicking the "Apply" button opens pop up to upload resume and submit application | 2 | Completed
| Backend: Implement POST /api/jobs/:jobId/apply to submit applications | 2 | Completed
| Determine best way to upload a file to a website and store it | 2 | Completed
| Create resume upload UI for candidates | 2 | Completed
| Restrict uploads to PDF/DOCX | 1 | Completed
| Backend: Implement Resume Upload API | 3 | Completed
| Backend: Store resume URLs | 3 | Completed
| Backend: Implement Resume Download API | 3 | Completed
| Frontend: Enable candidates to update skills, education, experience | 2 | Completed
SPRINT 3
Feature | Tasks | Expected Weightage | Actual Weightage | Status
Account Management | Add fields to add or update personal contact information, upload documentation and links to websites #126 | 1 | 1 | Completed
| Error Management #118 | 1 | 1 | Completed
| Unit and Integration Tests #181 | 2 | 2 | Completed
Candidate Portal | Frontend: Create "My Applications" page for candidates. #61 | 1 | -
| Backend: Implement GET /api/applications/:candidateId to fetch application status #62 | 3 | 1 | Completed
| Frontend: Add a "Save" button on job postings #64 | 2 | 1 | Completed
| Frontend: Create "Saved Jobs" page for candidates #65 | 2 | 2 | Completed
| Backend: Implement POST /api/jobs/:jobId/save to save jobs #66 | 3 | 1 | Completed
| Backend: Implement GET /api/jobs/saved to fetch saved jobs #67 | 2 | 1 | Completed
| Unit Testing and Integraton Testing | 3 | 5 | Completed
Employer Portal | Backend: API for Updating Application Status #72 | 2 | 2 | Completed
| Frontend: Allow the employer to view applicants details like resume, skills, education, experience #127 | 3 | 2 | Completed
| Unit Testing and Integraton Testing | 3 | 3 | Completed
Quizzes for Job Posting/ Screening Process | Frontend: Create a quiz creation form (MCQ questions), time limit and correct answers for auto-grading | 2 | 1 | Completed
| Backend: Create quizzes linked to the job posting #141 | 2 | 2 | Completed
| Frontend: Update create job posting form to include quiz selection and display attached quiz in job details view. #142 | 1 | 1 | Completed
| Backend: Modify Job model to store a reference to the quiz. #143 | 2 | 1 | Completed
| Frontend: When a user clicks “Apply” on job posting, display the quiz attempt page. #146 | 2 | 2 | Completed
| Backend: Fetch questions and store candidate responses with calculated score #147 | 3 | 3 | Completed
| Frontend: Create a Leaderboard page showing results for specific job #144 | 2 | 1 | Completed
| Backend: Fetch candidate responses & scores. #145 | 3 | 1 | Completed
| Quizzes Unit Test, Api Routes tests integrated with job creation #182 | 3 | 3 | Completed
Recommendation Engine | Make job categories field in database #148 | 2 | 1 | Completed
| Make frontend to display job categories #149 | 1 | 1 | Completed
| Allow users to enter preferred recommendations on profile creation #152 | 1 | -
| Create field in database for past applications #150 | 2 | 2 | Completed
| Create discover page to recommend jobs #151 | 2 | 1 | Completed
| Unit Testing and Integraton Testing | 2 | 2 | Completed
Search Engine | Backend: Modify jobPostings controller to accept an optional search query parameter and apply a regex‑based filter on key fields. #163 | 2 | 2 | Completed
| Frontend: In View Jobs page, add a state variable and insert a search input field above the job list. #164 | 2 | 1 | Completed
| Backend: Ensure the regex‑based filter in jobPostings controller includes the employer field. #165 | 2 | 1 | Completed
| Frontend: Leverage the existing search input and filtering logic in View Jobs page to filter job postings by employer name. #166 | 1 | 1 | Completed
| Backend: Update the search filter in jobPostings controller to also include the skills field. #167 | 1 | 1 | Completed
| Frontend: In View Jobs page, update the job interface and filtering logic to include the skills field. #168 | 2 | 1 | Completed
| Unit Testing and Integration Testing #171 | 2 | 1 | Completed

## Sprint 2 Analysis
SPRINT 2 REFLECTION
Feature | Tasks | Actual Weightage | Hours | Status
Account Management | Frontend: Sign up page UI | 2 | 2-3 | Completed | 1 | less than 1hr
| Backend: Implement Signup API (POST /auth/signup) with validation | 2 | 2-3 | Completed | 2 | 2-3 hrs
| Backend: Create a user with specific fields and save in DB | 1 | <1 | Completed | 3 | 4-6 hrs
| Backend: create verify email verification code and send email to use | 1 | <1 | Completed | 5 | 8-12 hrs
| Frontend: show UI page when user clicks on that link for success message | 1 | <1 | Completed | 8 | 1 day
| Frontend: Create Login Page UI with email and password fields fields | 2 | 2-3 | Completed | 13 | 2+ days
| Backend: Implement Login API (POST /api/auth/login) | 2 | 2-3 | Completed
| Frontend: Create Password Reset Page with email input | 1 | <1 | Completed
| Backend: Implement Reset Password API (POST /api/auth/reset-password) | 1 | <1 | Completed
| Frontend: Create New Password Page for updating the password | 1 | <1 | Completed
| Backend: Update user's password in DB | 1 | <1 | Completed
| Frontend: Logout Button | 1 | <1 | Completed
| Backend: Clear cookies on logout | 2 | 2-3 | Completed
| Backend: Implement Logout API (POST /api/auth/logout) | 2 | 2-3 | Completed
| Frontend: Redirect users to the login page after logout | 1 | <1 | Completed
| Frontend: Fetch user role from backend after login | 1 | <1 | Completed
| Frontend: Implement role-based navigation (Employer vs. Candidate) | 2 | 2-3 | Completed
| Frontend: Hide unauthorized features | 1 | <1 | Completed
| Backend: Store user roles in MongoDB | 1 | <1 | Completed
| Backend: Implement middleware to enforce role-based access control | 3 | 4-6 | Completed
| Frontend: Create Profile Page | 3 | 4-6 | Completed
| Backend: Implement User Profile API | 3 | 4-6 | Completed
| Backend: Store user details | 2 | 2-3 | Completed
Employer Portal | Frontend: UI for Job Posting Creation | 1 | <1 | Completed
| Backend: API for Job Posting | 2 | 2-3 | Completed
| Frontend: UI for Applicant Tracking | 2 | 2-3 | Completed
| API for Viewing Applicants | 2 | 2-3 | Completed
| Frontend: Enable employers to update company details | 2 | 2-3 | Completed
Candidate Portal | Frontend: Create UI for a page showing all available job postings | 1 | <1 | Completed
| Backend: Implement GET /api/jobs to fetch job postings | 2 | 2-3 | Completed
| Frontend: Add an "Apply" button on job postings | 1 | <1 | Completed
| Frontend: Clicking the "Apply" button opens pop up to upload resume and submit application | 2 | 2-3 | Completed
| Backend: Implement POST /api/jobs/:jobId/apply to submit applications | 2 | 2-3 | Completed
| Determine best way to upload a file to a website and store it | 2 | 2-3 | Completed
| Create resume upload UI for candidates | 2 | 2-3 | Completed
| Restrict uploads to PDF/DOCX | 1 | <1 | Completed
| Backend: Implement Resume Upload API | 3 | 4-6 | Completed
| Backend: Store resume URLs | 3 | 4-6 | Completed
| Backend: Implement Resume Download API | 3 | 4-6 | Completed
| Frontend: Enable candidates to update skills, education, experience | 2 | 2-3 | Completed

## Sprint 3 Analysis
SPRINT 3
Feature | Tasks | Expected Weightage | Actual Weightage | Status
Account Management | Add fields to add or update personal contact information, upload documentation and links to websites #126 | 1 | 1 | Completed | 1 | less than 1hr
| Error Management #118 | 1 | 1 | Completed | 2 | 2-3 hrs
| Unit and Integration Tests #181 | 2 | 2 | Completed | 3 | 4-6 hrs
Candidate Portal | Frontend: Create "My Applications" page for candidates. #61 | 1 | - |  | 5 | 8-12 hrs
| Backend: Implement GET /api/applications/:candidateId to fetch application status #62 | 3 | 1 | Completed | 8 | 1 day
| Frontend: Add a "Save" button on job postings #64 | 2 | 1 | Completed | 13 | 2+ days
| Frontend: Create "Saved Jobs" page for candidates #65 | 2 | 2 | Completed
| Backend: Implement POST /api/jobs/:jobId/save to save jobs #66 | 3 | 1 | Completed
| Backend: Implement GET /api/jobs/saved to fetch saved jobs #67 | 2 | 1 | Completed
| Unit Testing and Integraton Testing | 3 | 5 | Completed
Employer Portal | Backend: API for Updating Application Status #72 | 2 | 2 | Completed
| Frontend: Allow the employer to view applicants details like resume, skills, education, experience #127 | 3 | 2 | Completed
| Unit Testing and Integraton Testing | 3 | 3 | Completed
Quizzes for Job Posting/ Screening Process | Frontend: Create a quiz creation form (MCQ questions), time limit and correct answers for auto-grading | 2 | 1 | Completed
| Backend: Create quizzes linked to the job posting #141 | 2 | 2 | Completed
| Frontend: Update create job posting form to include quiz selection and display attached quiz in job details view. #142 | 1 | 1 | Completed
| Backend: Modify Job model to store a reference to the quiz. #143 | 2 | 1 | Completed
| Frontend: When a user clicks “Apply” on job posting, display the quiz attempt page. #146 | 2 | 2 | Completed
| Backend: Fetch questions and store candidate responses with calculated score #147 | 3 | 3 | Completed
| Frontend: Create a Leaderboard page showing results for specific job #144 | 2 | 1 | Completed
| Backend: Fetch candidate responses & scores. #145 | 3 | 1 | Completed
| Quizzes Unit Test, Api Routes tests integrated with job creation #182 | 3 | 3 | Completed
Recommendation Engine | Make job categories field in database #148 | 2 | 1 | Completed
| Make frontend to display job categories #149 | 1 | 1 | Completed
| Allow users to enter preferred recommendations on profile creation #152 | 1 | -
| Create field in database for past applications #150 | 2 | 2 | Completed
| Create discover page to recommend jobs #151 | 2 | 1 | Completed
| Unit Testing and Integraton Testing | 2 | 2 | Completed
Search Engine | Backend: Modify jobPostings controller to accept an optional search query parameter and apply a regex‑based filter on key fields. #163 | 2 | 2 | Completed
| Frontend: In View Jobs page, add a state variable and insert a search input field above the job list. #164 | 2 | 1 | Completed
| Backend: Ensure the regex‑based filter in jobPostings controller includes the employer field. #165 | 2 | 1 | Completed
| Frontend: Leverage the existing search input and filtering logic in View Jobs page to filter job postings by employer name. #166 | 1 | 1 | Completed
| Backend: Update the search filter in jobPostings controller to also include the skills field. #167 | 1 | 1 | Completed
| Frontend: In View Jobs page, update the job interface and filtering logic to include the skills field. #168 | 2 | 1 | Completed
| Unit Testing and Integration Testing #171 | 2 | 1 | Completed